## Sheet1
Category | Task | Notes/Contingencies
1. Event Definition | - Type of event (birthday, wedding, etc.). - Event objective. - Number of guests. | Adjust based on event type and guest count.
2. Date and Time | - Event date. - Start and end time. - Check the weather forecast (if outdoors). | Have a plan B in case of bad weather.
3. Location | - Confirm the event location. - Check capacity and accessibility. - Ensure parking availability. | Have an alternative location available.
4. Budget | - Define total budget. - Break down expenses by category (food, drinks, decoration, etc.). - Reserve 10-20% for contingencies. | Control and adjust as needed.
5. Invitations | - Create guest list. - Send invitations (digital or physical). - Track RSVPs. - Follow up with guests who haven't responded. | Consider sending via different channels (email, WhatsApp, etc.).
6. Food and Drinks | - Hire catering service or plan food preparation. - Arrange alcoholic and non-alcoholic beverages. - Consider special diets (vegetarian, vegan, gluten-free). | Have an alternative provider in case of failure.
7. Decoration | - Choose theme (optional). - List necessary decorative items (balloons, lights, flowers, etc.). - Decide whether to rent or DIY decorations. - Coordinate setup and takedown. | Bring extra tools for last-minute fixes.
8. Entertainment | - Hire a DJ, band, or prepare a playlist. - Organize games or activities (photobooth, contests). - Check technical equipment (sound, microphones). - Have a backup plan for technical issues. | Have portable speakers as a backup.
9. Logistics | - Check the number of chairs and tables. - Rent additional equipment (lights, microphones, etc.). - Assign storage space for gifts and other materials. - Coordinate post-event cleaning service. | Confirm all rentals before the event.
10. Contingency Plan (Plan B) | - Have tents or indoor locations in case of bad weather. - Hire a technician for sound or lighting issues. - Have backup providers. - Keep a first aid kit and emergency contacts handy. | Prepare emergency or accident protocols.
11. Day of the Event | - Confirm guest attendance. - Coordinate supplier arrivals. - Verify decoration and equipment setup. - Ensure activities and entertainment are ready. - Have contingency plans activated. | Assign responsible individuals for each task.
12. Post-event | - Perform venue cleanup. - Thank guests and suppliers. - Evaluate what went well and what could be improved for future events. | Retrieve all rented equipment and materials.